## Guidance
Peatland Code Risk Assessment Guidance (Version 1.2, 2021)
Step 1 | Identify potential hazards, specific to the project and project site that could impact the permanence of improved condition.
Step 2 | For each hazard identified score the likelihood (L) of its occurrence and the consequence (C) of its occurrence. Scores are as follows:
| Liklihood of Occurrence | Consequence of Occurrence:
| 1 = Very Unlikely | 1 = Insignificant
| 2 = Unlikely | 2 = Minor
| 3 = Fairly Likely | 3 = Moderate
| 4 = Likely | 4 = Major
| 5 = Very Likely | 5 = Catastrophic
Step 3 | For each hazard then calculate the risk (R) rating by multiplying (done automatically) the liklihood of occurrence score by the consequence of occurrence score. The risk rating key is as follows:
Risk Rating
13-25 = Unacceptable
9-12 = Tolerable
4-8 = Adequate
1-3 = Acceptable
Step 4 | Identify control measures to mitigate the risk of each identified hazard
Step 5 | Recalulate the risk rating post implementation of mitigation as per Step 2 and Step 3

## Risk Assessment
Peatland Code Risk Assessment (Version 1.2, 2021)
Hazard Categories | Identified Hazards and Impact on Permanence of Improved Condition (Add rows as necessary) | Risk Rating Without Controls |  |  | Mitigation Strategy | Risk Rating With Controls
|  | L | C | R |  | L | C | R
Restoration Activities |  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
Management Activities |  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
Extreme Weather |  |  |  | 0 |  |  |  | 0
Geological Events |  |  |  | 0 |  |  |  | 0
Fire |  |  |  | 0 |  |  |  | 0
Other |  |  |  | 0 |  |  |  | 0
13-25 = Unacceptable
9-12 = Tolerable
4-8 = Adequate
1-3 = Acceptable

## Example
Peatland Code Risk Assessment - Example (Version 1.2, 2021)
Hazard Categories | Identified Hazards and Impact on Permanence of Improved Condition (Add rows as necessary) | Risk Rating Without Controls |  |  | Mitigation Strategy | Risk Rating With Controls
|  | L | C | R |  | L | C | R
Restoration Activities | Dams not creating a hydrological seal with the base of the drain and water finding a new path through underneath the dam | 3 | 4 | 12 | Experienced Project Staff and contractors | 2 | 4 | 8
| Presence of peat pipes and sub-surface drainage | 2 | 3 | 6 | Where location known measures attempt made to disrupt/block | 1 | 3 | 3
| Incorrect seed material applied e.g. reprofiled hagg slope seeded with Sphagnum which may establish successfully on the lower portions of the slope where it is wetter but may fail on the upper portions of the slope due to drier conditions) | 3 | 4 | 12 | Revegetate with donor turves where available or introduce a mix of plants during revegetation (wet and dry species) | 2 | 4 | 8
| Reprofiled hagg too steep - soil and water movement preventing colonisation of introduced plants | 3 | 4 | 12 | Experienced Project Staff and contractors | 2 | 4 | 8
Management Activities | Scrub establishment leading to drying of peat | 2 | 2 | 4 | Removal of tree seedlings over 1m in height | 1 | 2 | 2
Extreme Weather | Hard frosts, storms, intense rainfall events could reverse attempts to re-vegetate e.g. wash brash and seeds off the soil surface. | 4 | 4 | 16 | Choose suitable vegetation mixture and revegetation method for climate | 2 | 4 | 8
Geological Events | Landslips/peat slides within restoration areaexposing areas of bare peat | 2 | 4 | 8 | Ensure restoration activities and methods minimise areas of unstable peat | 2 | 4 | 8
Fire | Uncontrolled muirburn or wildlifre removing vegetation | 2 | 4 | 8 | Cessation of muirburn on adjacent land | 1 | 4 | 4
Other | n/a |  |  | 0 |  |  |  | 0
13-25 = Unacceptable
9-12 = Tolerable
4-8 = Adequate
1-3 = Acceptable