## Guidance
Peatland Code Risk Assessment Guidance (Version 2.1, October 2024)
Step 1 | Identify potential risks, specific to the project and project site that could impact the permanence of improved condition, ecosystem services and local communites or other rights holders.
Step 2 | For each risk identified score the likelihood (L) of its occurrence and the consequence (C) of its occurrence. Guidance on the scores can be found in the Peatland Code Guidance document 2.1.
Step 3 | For each risk then calculate the total risk (R) rating by multiplying (done automatically) the likelihood of occurrence score by the impact of occurrence score. The risk rating key is as follows:
Risk Rating
13-25 = Unacceptable
9-12 = Tolerable
4-8 = Adequate
1-3 = Acceptable
Step 4 | Identify control measures to mitigate the total risk rating of each identified risk
Step 5 | Recalulate the risk rating post implementation of mitigation as per Step 2 and Step 3

## Risk Assessment
Peatland Code Risk Assessment (Version 2.1, October 2024)
Risk Categories | Risk sub-categories | Identified risks (Add rows as necessary) | Risk Rating Without Controls |  |  | Mitigation Strategy | Risk Rating With Controls
|  |  | L | I | R |  | L | I | R
Risk of Reversals | Restoration Activities |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
| Management Activities |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
| Extreme Weather |  |  |  | 0 |  |  |  | 0
| Geological Events |  |  |  | 0 |  |  |  | 0
| Fire |  |  |  | 0 |  |  |  | 0
| Other |  |  |  | 0 |  |  |  | 0
Risks to ecosystem services | Environmental impacts |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
| Impact on rare or endangered species |  |  |  | 0 |  |  |  | 0
| Impact on statutory designations |  |  |  | 0 |  |  |  | 0
| Impact on visual, cultural value and character of the local environment |  |  |  | 0 |  |  |  | 0
| Other |  |  |  | 0 |  |  |  | 0
Risks to local communities and other rights holders |  |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
13-25 = Unacceptable
9-12 = Tolerable
4-8 = Adequate
1-3 = Acceptable

## Example
Risk Categories | Risk sub-categories | Identified risks (Add rows as necessary) | Risk Rating Without Controls |  |  | Mitigation Strategy | Risk Rating With Controls
|  |  | L | I | R |  | L | I | R
Risk of Reversals | Restoration Activities | Dams not creating a hydrological seal with the base of the drain and water finding a new path through underneath the dam | 3 | 4 | 12 | Experienced Project Staff and contractors | 2 | 4 | 8
|  | Presence of peat pipes and sub-surface drainage | 2 | 3 | 6 | Where location known measures to attempt to disrupt/block | 1 | 3 | 3
|  | Incorrect seed material applied e.g. reprofiled hagg slope seeded with Sphagnum which may establish successfully on the lower portions of the slope where it is wetter but may fail on the upper portions of the slope due to drier conditions | 3 | 4 | 12 | Revegetate with donor turves where available or introduce a mix of plants during revegetation (wet and dry species) | 2 | 4 | 8
|  | Reprofiled hagg too steep - soil and water movement preventing colonisation of introduced plants | 3 | 4 | 12 | Experienced Project Staff and contractors | 2 | 4 | 8
[5 empty] | 0 |  |  |  | 0
| Management Activities | Scrub establishment leading to drying of peat | 2 | 2 | 4 | Removal of tree seedlings | 1 | 2 | 2
[5 empty] | 0 |  |  |  | 0
| Extreme Weather | Hard frosts, storms, intense rainfall events could reverse attempts to re-vegetate e.g. wash brash and seeds off the soil surface. | 4 | 4 | 16 | Choose suitable vegetation mixture and revegetation method for climate | 2 | 4 | 8
| Geological Events | Landslips/peat slides within restoration areaexposing areas of bare peat | 2 | 4 | 8 | Ensure restoration activities and methods minimise areas of unstable peat | 2 | 4 | 8
| Fire | Uncontrolled muirburn or wildlifre removing vegetation | 2 | 4 | 8 | Cessation of muirburn on adjacent land | 1 | 4 | 4
| Other | N/A |  |  | 0 |  |  |  | 0
Risks to ecosystem services | Environmental impacts | GHG emissions from the restoration works | 5 | 3 | 15 | Car share to the site, use local materials were possible | 4 | 2 | 8
[5 empty] | 0 |  |  |  | 0
| Impact on rare or endangered species | Damaging nesting sites of birds | 4 | 3 | 12 | Walkover surveys at appropriate time | 2 | 3 | 6
| Impact on statutory designations | Restoration plan goes against designation | 2 | 4 | 8 | Ensure necessary consents and advice are sought from statutory agency | 1 | 1 | 1
| Impact on visual, cultural value and character of the local environment | Damaging historic environmental heritage. | 2 | 4 | 8 | Carry out an archaeology assessment (desk based). Have archaeologist contact details if anything is encountered on site to seek appropriate guidance. Halt works until advice received | 1 | 3 | 3
| Other | N/A |  |  | 0 |  |  |  | 0
Risks to local communities and other rights holders |  | Access becomes more difficult, due to wetter conditions | 5 | 2 | 10 | N/A | 5 | 2 | 10
[5 empty] | 0 |  |  |  | 0
13-25 = Unacceptable
9-12 = Tolerable
4-8 = Adequate
1-3 = Acceptable